## Modules
ID # | Date | Module | Category | Defect Details | Suggestion for Fix | Ref Docs | Status | Due Date | Umm Clarification | Umm Test Status | Arun Comments 24.05.14 | Umm Comments - 2
1 | 2014-05-08 | Settings | Company Info | Financial Year Start & End should be Exactly 1 year | 1. Can be auto calculated if any one is set 2. Error Popping if not 1 yr |  | Open |  |  | Pass | Now its allowing Only 1 Yr + 1 Day Like 01 Jan to 01 Jan 1 Year should be 01 Jan to 31 Dec or 01 Aor to 31 Mar
2 | 2014-05-08 | Settings | Chart of Accounts Maintenance | 1. Default COA to be visible and non editable a. Foreign Exchange Gain/(Loss) accounts - 2 Nos b. Trade & Other Receivable & Creditors - 4 Nos (Earlier Arun Mentioned as Accounts Receivable & Payable, now the client want to keep as trade Receivable & Creditors only the name change, functionality all same) c. Discounts - 2 Nos d. Profit & Loss A/cs - 2 Nos (Only one Created) | a1. Unrealised Foreign Exchange Gain / (Loss) under Current Liabilities. a2. Foreign Exchange Gain/(Loss) under Expenses b1. Trade Receivables under Trade Receivables and mark the group non editable b2. Other Receivables under Other Receivables and mark the group non editable b3. Trade Payable under Trade Creditors and mark the group non editable b4. Other Creditors under new Group Other Creditors under Current Liabilities and mark uneditable c1. Discounts Given under Revenue c2. Discounts Received under Cost of Goods (If Client ok to offset in the Income / Expenses, I am fine, Then How to offset Prompt Payment Discounts) d1. Retained Earnings (Balance till end of Previous Financial Period Less Transfers) d2. Current Year Earnings - Current Period (This is the one we have created) both has to be created under the group Earnings under Surplus under Equity Note: none of the group / COA is editable) |  | Open |  |  | Pass | List as Discounts Given & Discounts Received Since Same Level of COA should not have same Name
3 | 2014-05-08 | Settings | Chart of Accounts Maintenance | 2. Option to Enter Opening Balances for Accounts | Can have it as the separate button like add account inside the COA Module where the user able to enter the Opening Balances for each COA and error check is kept for balancing figure errors |  | Open |  |  | Pass | This is not the way I asked, Refer Attached Sample (1003)
4 | 2014-05-08 | Settings | Chart of Accounts Maintenance | 3. Same Name can be created or modified at same level of COA | Error should be popped, if user try to create or edit the same name for 2 items under same level |  | Closed |  |  | Pass
5 | 2014-05-08 | Settings | Chart of Accounts Maintenance | 4. Client says COA given by them and the Default COA inside the S/w differs in few places (Eg: Fixed Assets) | Cross Check the List against each other |  | Open
6 | 2014-05-08 | Settings | Chart of Accounts Maintenance | 5. Sales Tax Accounts not Created automatically when we create tax codes | Sales Tax A/c to be auto created under Taxes group when ever we create a Tax code |  | Open
7 | 2014-05-09 | Settings | Chart of Accounts Maintenance | 6. Payment / Accruals Account option available for non required items as well and its confusing during data entry | 1. Need to find the logic behind these 2. Arun has to talk to YC and ask for the purpose and explain it is automatically taken care by AP & AR modules 3. To remove this option after acceptance from client |  | Open |  |  | Pass | A. In Add Customer 1. No need to list New Additions Seperately 2. No Multiple Selection shd be allowed Allowed 3. We have it as simple as adding New Cutomer or Product in Invoice B. In Invoice Creation 4. If Cash Terms Selected, display on the Cash and Cash Equivalent Items no need to display Others Ref Attached - 1007a & 1007b
8 | 2014-05-09 | Settings | Chart of Accounts Maintenance | 7. If the number of COA inside one particular group is more than 99, what code will be assigned to the 100th One (I tried using import Function say successfully imported except 2 but its not inside) | Error Msg saying reached maximum | 008a 008b | Open
9 | 2014-05-09 | Settings | Chart of Accounts Maintenance | 8. Change the "Operating Income" Group to Non Operating Income in default COA |  |  | Closed |  |  | Pass
10 | 2014-05-09 | Settings | Chart of Accounts Maintenance | 9. Following Groups should be Non Editable Current Assets Cash & Cash Equivalents Trade Receivables Other Receivables Non-Current Assets Current Liabilities Trade Creditors Non-Current Liabilities Revenue Non-Operating Income Other Income Cost of Goods Operating Expenses Non-Operating Expenses | Make it Uneditable so that the reports will carry Names used for reports |  | Closed |  |  | Pass
11 | 2014-05-09 | Settings | List of Products and Services | Could not able to delete a product following error SQLSTATE[42S02]: Base table or view not found: 1146 Table 'ummtech1_accounting_45.SqlErrors' doesn't exist |  |  | Open |  |  | Pass
12 | 2014-05-09 | Settings | List of Products and Services | Each Product should have unique ID & Name | Since It will be confusing while creating Invoices |  | Open |  |  | Pass
13 | 2014-05-09 | Settings | Invoice and Credit Note Customization | 1. Not able to Check the Display Logo Check Box 2. What is the difference between 3 Templates |  | 013 | Open |  | Removed this option. So if the logo uploaded by default it will display logo |  | To Check how is Works on the call
14 | 2014-05-09 | Settings | Invoice and Credit Note Customization | 3. Prefix for Credit Note not able to configure | Include in the Customisation Screen |  | Closed |  |  | Pass
15 | 2014-05-09 | Settings | Tax Code Table | 1. Header shd be "Tax Codes" Remove "for Purchases" |  | 015 | Closed |  |  | Pass
16 | 2014-05-09 | Settings | Tax Code Table | 2. Not able to configure as the Input or Output Tax | Option to be provided while adding a tax code (Which has to used for creating Tax Report) |  | Closed |  |  | Pass
17 | 2014-05-09 | Settings | Tax Code Table | 3. Add Category of Tax Type while listing |  |  | Open |  |  | Pass | Description is Same for all Type of TX Code, shd display the Desc as in the IRAS Appedix
18 | 2014-05-09 | Settings | Notifications | Not Developed Yet |  |  | Open
19 | 2014-05-09 | Settings | Theme Manager | Not Developed Yet |  |  | Open
20 | 2014-05-09 | Settings | Language Option | Not Developed Yet |  |  | Open
21 | 2014-05-09 | Settings | Restore/Delete Account | Not Developed Yet |  |  | Open
22 | 2014-05-09 | Settings | Import Data | Import Chart of Accounts - Not Working | Customer, Vendor & Product Import Ok | 022a 022b | Open |  |  | Pass | 1. Importing but Opening Balance is not getting uploaded 2. Need to have same check for Opening Balance Concept
23 | 2014-05-09 | Settings | Import Data | Import of Transactions - Not Developed Yet | TO be Created for 3 major Modules Invoice, Income & Expenses Note: Voucher Number to be issued by the System |  | Open
24 | 2014-05-09 | Settings | User Profiles | Admin able to Create Developer User - Logically Wrong |  |  | Closed |  |  | Pass
25 | 2014-05-09 | Settings | User Profiles | Not able to Change User Type - Eg: If any User got Promoted as Manager |  |  | Closed |  |  | Pass
26 | 2014-05-09 | Settings | Process Control | Not Developed Yet |  |  | Open
27 | 2014-05-09 | Settings | Audit Trails | 1. No options to filter on what to view | Create Filers for Transaction Log, System Logs, etc with All / modified / Deleted |  | Open |  |  | Pass | Design Looks Good, Arun need to Test
28 | 2014-05-09 | Settings | Audit Trails | 2. Print and Export Options Missing |  |  | Closed |  |  | Pass
29 | 2014-05-09 | Settings | Audit Trails | 3. List Oldest on top |  |  | Closed |  |  | Pass
30 | 2014-05-10 | Settings | Forign Exchange Rates | How do we configure Foreign Exchange Rates |  |  | Open
31 | 2014-05-10 | Dashboard |  | Not Developed Yet |  |  | Open
32 | 2014-05-10 | Invoice / Credit | Invoice / Credit Note Summary | Following actions missing a. Print b. Send c. Export as PDF |  |  | Open
33 | 2014-05-10 | Invoice / Credit | Add Invoice | What does the following options do, Not tested Yet a. Prompt Payment Discount b. Non Revenue Supply (Tax) | After getting to know have to Test - Action by Arun |  | Open |  | What this mean? This options will not affect anywhere in transaction |  | a. As discussed these Discount should be Discounts Given and hit COA b. They why the oprion is there
34 | 2014-05-10 | Invoice / Credit | Add Invoice | Due date can be changed irrespective of Credit Term we choose. What does the duedate do to the system |  |  | Open
35 | 2014-05-10 | Invoice / Credit | Add Credit Note | It allows Items & Qty not in Invoice | It shd be allowed to create if only the Items in the Original Invoice is there and the qty should not exceed even 1 or more CN is issued |  | Open
36 | 2014-05-10 | Invoice / Credit | Add Credit Note | Discount column is not there for Items we gave discount in the Original Invoice | Discount column to be added and should do exactly opp of what its doing in Add Invoice |  | Open
37 | 2014-05-10 | Invoice / Credit | Add Credit Note | Non-Revenue Supply (Tax) is also missing | If its there in Invoice it should also be in CN as well |  | Open
38 | 2014-05-10 | Invoice / Credit | Add Credit Note | Admin not able to approve on the spot Need to submit for approval and then has to approve | Make it how its in Add Invoice, approval can be done at the time of creation itself |  | Open
39 | 2014-05-10 | Invoice / Credit | Add Invoice & Credit Note | If 2 Invoices created at the same time, Invoice No Generated on both the Screen is same and it changes to next for which is saved later (Its not a bug but misleading if user take note of the number and used the same for later purposes eg: creating Credit note or payment, etc) | Come back on this after discussing with Lakshmanan |  | Closed |  |  | Pass
40 | 2014-05-10 | Invoice / Credit | Add Invoice & Credit Note | If products of different currency added the total shows sum of 2 currencies (Confusing on the logic - Need Briefing) |  |  | Open |  | Rectified only in invoice. Credit note in progress | In Progress
41 | 2014-05-10 | Invoice / Credit | Add Invoice & Credit Note | Tax Code Calculations yet to check after fixing the error in creation |  |  | Open
42 | 2014-05-10 | Income | Add Income | It accepts Duplicate Receipt Numbers | Each Receipt Should have unique Receipt Numbers |  | Open |  |  | Pass | Arun Yet to Test
43 | 2014-05-10 | Income | Add Income | For Prompt Payment Discount What is the Double Entry I tried with the Discount But No Effect |  |  | Open |  |  | Pass | Arun Yet to Test
44 | 2014-05-10 | Income | Add Income | Again Payment / Accural Account - what is the use |  |  | Open |  |  | Pass | Arun Yet to Test
45 | 2014-05-10 | Income | Add Income | If we choose Foreign Currency how the calcuations done |  |  | Open |  |  | Pass | Arun Yet to Test
46 | 2014-05-10 | Expenses | Add Expenses | No need for Shipping Addresses |  |  | Open |  |  | Pass | Arun Yet to Test
47 | 2014-05-10 | Expenses | Add Expenses | Permit No - Why this is Added |  |  | Open |  | Client asked this option to be added | Pass | Arun Yet to Test
48 | 2014-05-10 | Expenses | Add Expenses | Payment / Accruals Account | - Do - |  | Open |  |  | Pass | Arun Yet to Test
49 | 2014-05-10 | Expenses | Add Expenses | Prompt Payment Discount | - Do - |  | Open |  |  | Pass | Arun Yet to Test
50 | 2014-05-10 | Expenses | Add Expenses | If the Payment Terms Selected as "Cash" like in Invoice / Income the Payment Particulars to be asked where user enter the details |  |  | Open |  |  | Pass | Arun Yet to Test
51 | 2014-05-10 | Customers | Add New Customer | COA Link Account not specified here | Create a Tab for this with the 2 options Trade Receivables & Other Receivables And link the Closing balances for each COA correspondingly |  | Open |  |  | Pass | Arun Yet to Test
52 | 2014-05-10 | Vendors | Ass New Vendor | COA Link Account not specified here | Create a Tab for this with the 2 options Trade Creditors & Other Other Creditors And link the Closing balances for each COA correspondingly |  | Open |  |  | Pass | Arun Yet to Test
53 | 2014-05-10 | Journal Entries | List of Jrnl Entry | No Print & Export avaliable in Action List |  |  | Open
54 | 2014-05-10 | Settings | Tax Code Table | Not able to Activate the Tax Codes |  |  | Closed |  |  | Pass
55 | 2014-05-10 | Reports | Balance Sheet | Not Developed Fully | Add the Below to the Discussion we had earlier 1. Retained Earnings shd also be reflected together above Current Year Earnings 2. No Accounts Receivable, its Trade Receivables & Other Receivables 3. No Accounts Payable, its Trade Creditors & Other Creditors 4. Sample Attached (Red Colour are Default ones) | 055 Balance Sheet Sample.xlsx | Open
56 | 2014-05-11 | Reports | Income Statement | Need Some Changes to Existing | 1. Since we changing Operating Expenses to Non Operating Expenses, it need to be pushed after Gross Profit 2. Sample Attached (Red Colour are Default ones) | 056 Income Statement Sample.xlsx | Open
57 | 2014-05-11 | Reports | Cash Flow Statement | Change Name to "Cash Flow Analysis" |  |  | Open
58 | 2014-05-11 | Reports | Cash Flow Statement | Still Not Generating Properly | 1. Follow what we discussed on this earlier 2. Follow the COA Format to List Inflow & Outflow |  | Open
59 | 2014-05-11 | Reports | Bank Reconciliation | Not Developed Yet | Client want both Manual & Import Options 1. Follow what we discussed on this earlier to create the Manual Report 2. For Import Option, consider the following a. after Import Items with Same Reference Number & Amounts Reconcile automatically b. The Open Items from the Bank Statement Lists on the left side and user select each one of it then the corresponding or items from our books isted on the right side for the User to choose c. Report should be auto Generated d. If User could not able to identify any open items, Try to minimise redoing the matching process done so far e. After user confirm at the end, then only it should be get posted |  | Open
60 | 2014-05-11 | Reports | IRAS Audit File | Following were missing in the report 1. Count Total, GSTtotal & Base Total in Purchases & Supllies 2. Total Count, Currency in GL, Total Cr. & Total Dr. in the Transactions List | 1. Company infor is Clear 2. Purchases - All Expenses Transactions 3. Supplies - All Transactions in Invoice / Cedit Note & Income 4. GL Data - Includes 2 & 3 + Tranasactions trough Journal Entries |  | Open
61 | 2014-05-11 | Reports | IRAS Audit File | When Exported to Excel Cutomer Listing & Vendor Listing is exported instead of Supplies & Purchases Listing |  |  | Open
62 | 2014-05-11 | Reports | Sales Tax Report | Not Developed Yet | 1. List all the Sales and Purchases Trasactions seperately sorted by each tax code 2. Totals should be available for selected period for each tax code |  | Open
63 | 2014-05-11 | Reports | Ageing Report - Receivables | Not Completed | 1. Follow what we discussed on this earlier 2. If I click a customer, list of outstanding invoices to be listed in below or in separate page |  | Open
64 | 2014-05-11 | Reports | Ageing Report - Payables | Not Completed | 1. Follow what we discussed on this earlier 2. If I click a Vendor, list of outstanding invoices to be listed in below or in separate page |  | Open
65 | 2014-05-11 | Reports | General Ledger | Not Completed | To include the following in the Existing 1. Opening Balance 2. Running Balance 3. Closing Balance 4. Sort Gl by Name 5. Sort by Date for each GL 6. For Income & Expenses Accounts - Opening Balnce will be there only for the period choosen between fiancial year 7. List only GL A/c which had tranactions or closing balance | 065 General Ledger Sample.xlsx | Open
66 | 2014-05-11 | Reports | Income By Customer | Not Completed | 1. If user click the customer name, breakdown of income should be given based on COA sort (Either dropdown or in new tab) |  | Open
67 | 2014-05-11 | Reports | Expenses by Vendor | Not Completed | 1. If user click the Vendor name, breakdown of Expenses should be given based on COA sort (Either dropdown or in new tab) |  | Open
68 | 2014-05-11 | Reports | Account Transactions | Not Completed | Exactly like General Ledger Reort but list only for 1 particular account |  | Open
69 | 2014-05-11 | Reports | Gain / Loss on Foreign Currency | Not Developed Yet | 1. Take the logic what we discussed on 10.05.14 (have a check box for Foreign currecy payment to indicate full payment and calculate gain / loss accordingly) |  | Open

## General
ID # | Date | Module | Category | Defect Details | Suggestion for Fix | Ref Docs | Status | Due Date | Umm Clarification | Umm Test Status | Improvement for our Product
G1 | 2014-05-09 | All | Navigation | 1. If the new window opens in the same tab, there no back button to go back to previous Level 2. If New tab opens there is no option to close the tab and return to the tab where left off |  |  | Open
2 | 2014-05-09 | All | Sort | Sort Button no near the respective Headers |  |  | Open
3 | 2014-05-10 | All | Foreign Exchange Differences | Not sure how it works & How the calculations are made | Create Category in the Settings & Allow Users to Create with Exchange Rate - Only the user created list will apear in all modules |  | Open
4 | 2014-05-10 | Reports | All | No need to add text "Company" behind the Company Names, just display the company name entered in the company Info |  |  | Open
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
Formulas:
Date = +[Date, row above]

## Sheet1
Open | Yet to Start
Re Open | In Progress
Closed | Pass
WIP | Fail
Hold | Pending for Clarification
Rejected